## Read me
Hospital Appointment & Patient Management System
User story backlog and sprint plan · Advanced Python major assignment · Due 21 October 2026
How to use this file
1 | Open the 'User Stories' sheet. Every row is one story with its acceptance criteria.
2 | Fill only the yellow columns: Points, Owner, Sprint, Status. They have drop-down lists.
3 | The 'Sprint Plan' sheet adds everything up by itself. Do not type into its white cells.
4 | Update Status at the end of each working session so the progress figures stay true.
Story points
1 | Trivial, under an hour
2 | Small, half a day
3 | Normal, about one day
5 | Large, two days, worth splitting if possible
8 | Very large, needs design first
Priority (MoSCoW)
Must | Tier 1 and 2 in the PRD. The project fails without it.
Should | Valuable but the demo survives without it.
Could | Tier 3 bonus. Build only if ahead of schedule; otherwise write it up as a future enhancement.
Rule
Code freeze | 16 October. After that date no new story is started; only bug fixes, report and slides.

## User Stories
Product backlog
Yellow columns are yours to fill in. Everything else is set by the PRD.
Story ID | Epic | As a... | I want... | So that... | Acceptance criteria | PRD ref | Priority | Points | Owner | Sprint | Status
US-01 | Foundation | developer | a shared Git repo with the folder structure and schema.sql | everyone can start coding without overwriting each other | Repo cloned by all 4; running schema.sql creates 10 tables with no error | — | Must | 3 | Person 1 | Sprint 1 | Not started
US-02 | Foundation | developer | a database module that opens the connection and creates tables | every other module has one way to reach the data | init_db() is safe to run twice; foreign keys are ON | — | Must | 2 | Person 1 | Sprint 1 | Not started
US-03 | Foundation | developer | the model classes Person, Patient, Doctor and Appointment | the team shares one definition of every object | Patient and Doctor inherit Person and override display_info(); age has a validating setter | — | Must | 5 | Person 1 | Sprint 1 | Not started
US-04 | Foundation | developer | reusable input helpers for text, numbers, phone, date and time | no menu ever crashes on bad typing | Letters typed into a number field re-prompt instead of raising | — | Must | 3 | Person 2 | Sprint 1 | Not started
US-05 | Foundation | developer | a seed script that fills the database with demo data | we can test and demo without typing records by hand | 3 departments, 6 doctors, 20 patients, 30 appointments created by one command | — | Must | 3 | Person 2 | Sprint 1 | Not started
US-06 | Authentication | staff member | to log in with a username and password | patient data is not open to anyone who opens the program | Correct login opens the menu; 3 wrong attempts exit; passwords stored as SHA-256 | FR-1.1 | Must | 3 | Person 1 | Sprint 1 | Not started
US-07 | Authentication | user | to see only the menu options my role allows | staff cannot reach functions they should not use | Receptionist login shows no admin options; doctor login shows only their own appointments | FR-1.2 | Must | 3 | Person 1 | Sprint 1 | Not started
US-08 | Authentication | admin | to create, deactivate and reset user accounts | staff changes do not need a developer | New account can log in; deactivated account is refused | FR-1.3 | Should | 3 | Person 1 | Sprint 2 | Not started
US-09 | Patients | receptionist | to register a new patient with an auto-generated ID | each patient is identified once and never duplicated | ID follows P001, P002; name and phone are required; created_at is stored | FR-2.1 | Must | 3 | Person 2 | Sprint 2 | Not started
US-10 | Patients | receptionist | to update a patient's details | records stay correct when a phone number or address changes | Any field except the ID can be changed; validation runs again on the new value | FR-2.2 | Must | 2 | Person 2 | Sprint 2 | Not started
US-11 | Patients | receptionist | to search patients by ID, part of the name, or phone | I can find a returning patient in seconds | Partial name matches; no match prints a message, not an error | FR-2.3 | Must | 3 | Person 2 | Sprint 2 | Not started
US-12 | Patients | receptionist | to list all patients in a formatted table | I can see the register at a glance | Columns aligned; long lists paged 20 at a time | FR-2.4 | Must | 2 | Person 2 | Sprint 2 | Not started
US-13 | Patients | admin | to delete a patient only when they have no appointments | history is never orphaned | Delete with appointments is refused and explains why | FR-2.5 | Must | 2 | Person 2 | Sprint 2 | Not started
US-14 | Patients | doctor | to see one patient's full visit history | I know what was diagnosed before I treat them | Visits listed newest first with doctor, diagnosis and total | FR-2.6 | Should | 3 | Person 2 | Sprint 3 | Not started
US-15 | Doctors | admin | to add, update and list departments | doctors can be grouped and reported on by department | Department name is unique; a department with doctors cannot be deleted | FR-3.1 | Must | 2 | Person 3 | Sprint 2 | Not started
US-16 | Doctors | admin | to register a doctor under a department with a consultation fee | bookings can calculate a fee automatically | Doctor ID follows D001; fee cannot be negative; department must exist | FR-3.2 | Must | 3 | Person 3 | Sprint 2 | Not started
US-17 | Doctors | receptionist | to search doctors by name, specialization or department | I can find the right doctor for a patient's problem | Search on any of the three fields returns matching active doctors | FR-3.3 | Must | 2 | Person 3 | Sprint 2 | Not started
US-18 | Doctors | admin | to deactivate a doctor rather than delete them | past appointments keep a valid reference | Deactivated doctor cannot be booked but still appears in old records and reports | FR-3.4 | Must | 2 | Person 3 | Sprint 2 | Not started
US-19 | Doctors | admin | to define each doctor's weekly shifts | the system knows when a doctor is actually available | Shift stores day, start, end and slot length; overlapping shifts are refused | FR-3.5 | Must | 5 | Person 3 | Sprint 3 | Not started
US-20 | Appointments | receptionist | to see the free time slots for a doctor on a date | I can offer the patient a real choice instead of guessing | Slots built from the shift minus booked times; no shift that weekday prints a clear message | FR-4.1 | Must | 8 | Person 3 | Sprint 3 | Not started
US-21 | Appointments | receptionist | to book an appointment into a free slot | the visit is recorded with its fee | Appointment saved with status Booked and the doctor's fee copied onto it | FR-4.2 | Must | 5 | Person 4 | Sprint 2 | Not started
US-22 | Appointments | receptionist | the system to refuse a slot already taken | two patients never arrive for the same time | Second booking refused; sqlite3.IntegrityError caught and shown as a sentence | FR-4.3 | Must | 3 | Person 4 | Sprint 2 | Not started
US-23 | Appointments | receptionist | the system to refuse past dates and non-working days | the schedule stays realistic | Yesterday refused; a day with no shift refused; today allowed only for later times | FR-4.4 | Must | 3 | Person 4 | Sprint 3 | Not started
US-24 | Appointments | receptionist | to cancel an appointment | the slot can be given to someone else | Status becomes Cancelled and the slot reappears as free; completed visits cannot be cancelled | FR-4.5 | Must | 2 | Person 4 | Sprint 3 | Not started
US-25 | Appointments | doctor | to mark an appointment completed | the visit moves on to its record and invoice | Status becomes Completed and both the record and the invoice are created | FR-4.6 | Must | 3 | Person 4 | Sprint 3 | Not started
US-26 | Appointments | receptionist | to list appointments by date, doctor or patient | I can answer questions at the desk immediately | Each filter prints a formatted table; empty result prints a message | FR-4.7 | Must | 3 | Person 4 | Sprint 3 | Not started
US-27 | Appointments | receptionist | to mark a missed appointment as No-show | statistics separate cancellations from people who did not arrive | Status No-show; the visit appears in reports but creates no invoice | FR-4.8 | Should | 1 | Person 4 | Sprint 3 | Not started
US-28 | Records | doctor | to write symptoms, diagnosis, treatment and a follow-up date | the next visit starts from what happened last time | One record per completed appointment, enforced by UNIQUE | FR-5.1 | Must | 3 | Person 4 | Sprint 3 | Not started
US-29 | Records | doctor | to prescribe medicines from the stock list | the patient leaves with the right medication on the receipt | Prescription lines store quantity and the price at time of issue | FR-5.2 | Could | 5 | Person 4 | Sprint 4 | Not started
US-30 | Records | pharmacist | stock to fall automatically when medicine is prescribed | the stock figure is always true | Quantity above stock is refused and nothing is written | FR-5.3 | Could | 3 | Person 4 | Sprint 4 | Not started
US-31 | Records | admin | to be warned about low stock and near-expiry medicine | we reorder before running out | Warning when stock is at or below reorder level, or expiry is within 30 days | FR-5.4 | Could | 2 | Person 3 | Sprint 4 | Not started
US-32 | Billing | receptionist | an invoice created automatically when a visit is completed | nobody adds up the bill by hand | Consultation fee + medicines + $5 service charge − discount, stored on the invoice | FR-6.1 | Must | 5 | Person 4 | Sprint 3 | Not started
US-33 | Billing | patient | the age discount applied automatically | children and seniors are charged correctly every time | 10% off the consultation fee under 5 and over 60; zero otherwise | FR-6.2 | Must | 2 | Person 4 | Sprint 3 | Not started
US-34 | Billing | receptionist | to mark an invoice Paid with a method and timestamp | the day's takings can be reconciled | Status Unpaid to Paid; paid_at recorded; an unpaid invoice appears in the unpaid report | FR-6.3 | Must | 2 | Person 4 | Sprint 3 | Not started
US-35 | Billing | patient | a printed receipt for my visit | I have proof of what I paid | Receipt shows the breakdown, prints to screen and to data/receipts/<id>.txt | FR-6.4 | Must | 3 | Person 1 | Sprint 3 | Not started
US-36 | Reports | receptionist | today's appointment sheet | the desk knows who is coming before the clinic opens | Lists time, patient, doctor and status for the current date | FR-7.1 | Must | 2 | Person 1 | Sprint 4 | Not started
US-37 | Reports | admin | income by doctor and by department for a date range | I can see which part of the clinic earns what | Totals match the sum of paid invoices in that range; exportable to CSV | FR-7.2 | Must | 3 | Person 4 | Sprint 4 | Not started
US-38 | Reports | admin | to see the busiest doctor and the busiest weekday | staffing can be planned from real numbers | Ranked list built from completed appointments | FR-7.3 | Should | 2 | Person 3 | Sprint 4 | Not started
US-39 | Reports | admin | a list of unpaid invoices | no visit is forgotten at the cashier | Lists invoice, patient, amount and days outstanding | FR-7.4 | Should | 2 | Person 3 | Sprint 4 | Not started
US-40 | Reports | admin | an audit log of who changed what | mistakes can be traced to a person and a time | Every delete and deactivate writes a row with username, action and timestamp | FR-7.6 | Could | 3 | Person 1 | Sprint 4 | Not started
US-41 | Delivery | team | to run all 24 test cases and record the results | the report shows the system was actually tested | Every test case in the PRD has a pass or fail and a screenshot | — | Must | 5 | All | Sprint 4 | Not started
US-42 | Delivery | team | the report written in the required book format | the submission meets the lecturer's formatting rules | Cover to references in order; Times New Roman; margins 1.5/1.5/1.5/3 cm; spacing 1.15 | — | Must | 8 | All | Sprint 4 | Not started
US-43 | Delivery | team | 10 to 15 slides and a rehearsed live demo | the presentation runs without surprises | Demo rehearsed twice on seeded data; every member can answer on their own module | — | Must | 5 | All | Sprint 4 | Not started
[7 empty] | Total points | 137
[7 empty] | Done points | 0
[7 empty] | Complete | 0%

## Sprint Plan
Sprint plan
Five weeks, four people. Planned, done and remaining points are calculated from the User Stories sheet.
Sprint | Goal | Start | End | Weeks | Capacity (pts) | Planned (pts) | Done (pts) | Remaining | % complete | Load vs capacity
Sprint 1 | Foundation: database, classes, login, menu skeleton | 28 Sep | 4 Oct | 1 | 40 | 22 | 0 | 22 | 0% | 55%
Sprint 2 | Core records: patients, doctors, departments, first bookings | 5 Oct | 11 Oct | 1 | 40 | 32 | 0 | 32 | 0% | 80%
Sprint 3 | Appointments, schedules, billing and records | 12 Oct | 16 Oct | 2 | 40 | 43 | 0 | 43 | 0% | 107.5%
Sprint 4 | Bonus features, testing, report, slides, submission | 17 Oct | 21 Oct | 3 | 40 | 40 | 0 | 40 | 0% | 100%
Total |  |  |  |  | 160 | 137 | 0 | 137 | 0%
Points per person per sprint
Person | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Total
Person 1 | 16 | 3 | 3 | 5 | 27
Person 2 | 6 | 12 | 3 | 0 | 21
Person 3 | 0 | 9 | 13 | 6 | 28
Person 4 | 0 | 8 | 24 | 11 | 43
All | 0 | 0 | 0 | 18 | 18
Capacity is an estimate: 4 people x about 10 points a week. Change the yellow cells once you know your real pace.
Load above 100% means the sprint is overbooked: move a Could story to a later sprint or drop it.